## Sheet1
Sr. No | Date | Time | Location | Attendees | Absentees | Agenda | Decisions Made | Action Items | Key points
1 | 2025-11-05 | 9:30 | CS Faculty Offices | Hammad Shabbir, Hasnain Ali, Ahmer Sultan Abdul Rafay (RP) | None | Project idea generation discussion and decision | Project decided and approved | Team to prepare development Agreement and project proposal | Multiple projects discussed browser and timetable management system shortlisted timetable management system chosen
2 | 2025-12-15 | 10:30 | Academic Block | Hammad Shabbir, Hasnain Ali, Ahmer Sultan Abdul Rafay (RP) | None | Get the requirements of the system | High Level requirements finalized | Team to prepare detailed SRS document for the system | Requirements discussed, Assigned team with the tasks